## Road
Revised Proposed Procurement Plan(PPP) - 2019
Dept:-Divisional Secretariat-Jaffna
Department Line Agency / Ministry | Type Of Procurement (Goods, Works,Equipment & Service etc,) | Estimated Cost (Rs.Mn) | Source of Financing Name of the Donor | Procurement method (ICB,NCB)AND Shopping Procedure etc) | Level of authority(CAPC,MPC,DPC,PPC,etc.) | Priority Status U= Urgent P= Priority N=Normal | Current Status of Procurement Preparedness activities | Scheduled date of commencement | Scheduled date of completion | Remarks
Gamperaliya (104-2-6-20-2506)
Works
1 | Renovation of Vasanthapuram cross road, Colombuthurai 1st lane, 3rd cross road, Valanpuram 9th cross road, Valanpuram Temple Road and AV Road sub lane | 4209858.5 | CF | NCB | RPC | N | Completed | 2019.05.27 | 2019.07.30
2 | Renovation of Muththaiya Bakery lane, Colombuthurai road cross lane, Pettrer lane and Co - oprative bylane, Kachcheri Nallur post office lane, Kachcheri nallur sub lane, Maruthady lane 6th cross and Maruthady 2nd cross road. | 4065051.7 | CF | NCB | RPC | N | Completed | 2019.05.27 | 2019.07.30
3 | Renovation of Rajendra road, St.James east road, St.James lane, Sinnakadai road, old park sub road and Pillaiyar 7th cross road | 4083373.5 | CF | NCB | RPC | N | Completed | 2019.05.27 | 2019.07.30
4 | Renovation of Muslim college cross road, Katkulam cross road, Nawanthurai school back lane (side road), Kalaivani community centre playground near road, Kannapuram 1st, 2nd, and 3rd lanes, Kannapuram 4th and 5th lanes, and Manpiddy 1st, 2nd lane Kannapuram | 3447377.5 | CF | NCB | RPC | N | Completed | 2019.05.27 | 2019.07.30
5 | Renovation of Beach Road, NMS Lane, Navalar Road and Seliyan Road Sub Lane. | 2391379.5 | CF | NCB | RPC | N | Completed | 2019.05.27 | 2019.07.30
6 | Renovation of Thurayappa Maha Vidi.Ground Drainage path way work, Muthlikkulam outlet channel work, Old park road channel work, Thevarikkulam outlet drainage channel work, Maruthady road drainage channel work | 3869058.34 | CF | NCB | RPC | N | Completed | 2019.05.27 | 2019.07.30
7 | Renovation of Pointpedro road 1st lane drainage work, Temble road sub lane drainage channel wall work, Menadchchi amman road drainage channel wall work St.Partick's road drainage turn out work, 2nd cross road (sea side) drainage channel work | 4558335.76 | CF | NCB | RPC | N | Completed | 2019.05.27 | 2019.07.30
8 | Renovation of Kannathiddy drainage channel wall work, Villundri tempe road drainage channel work | 3785570.8 | CF | NCB | RPC | N | Completed | 2019.05.27 | 2019.07.30
9 | Renovation of Konanthodda road drainage channel wall work and Araly road drainage channel work to Rajalikulam | 4343072.8 | CF | NCB | RPC | N | Completed | 2019.05.27 | 2019.07.30
10 | Renovation of nedunkulam drainage channel (Katheeja school Katkulam channel) wall work and kalaivani ground east side drainage channel work | 2828117.75 | CF | NCB | RPC | N | Completed | 2019.05.27 | 2019.07.30
11 | Renovation of 2nd Cross internal road at Passaiyoor, Punkankulam sub Lane, Punithapuram West Road, Punithapuram North Road | 4349639.36 | CF | NCB | RPC | N | Completed | 2019.06.25 | 2019.08.25
12 | Renovation of 3rd Cross by Lane at Eachamoddai, 6th and 7th Cross road Echchamodai , Kadatkarai Road at Echamoddai, Plaches lane 2nd Cross road, Old Park Road 1st,2nd,3rd and 4th Lanes | 4033565.02 | CF | NCB | RPC | N | Completed | 2019.05.24 | 2019.08.17
13 | Renovation of 3rd Cross at Passaiyoor, Madam road, Nedunkulam 8th Lane, Paalkulam 1st,2nd Lanes, Koyathoddam New Road1st,2nd Lanes, vidance Lane | 4294508.89 | CF | NCB | RPC | N | Completed | 2019.05.24 | 2019.08.17
14 | Renovation of concrete road for Hospital Road South lane, Chippitharai Road, Mathews road sub road 1, Rajasingam Road by lane, Water Tank 5th Cross Lane, Rajendra Road Patricks Road Link Road, Cathedral Lane, Pointpedro road 1st cross. | 4459057.23 | CF | NCB | RPC | N | Completed | 2019.05.24 | 2019.08.17
15 | Renovation of Mathews road sub road 2, St. Martin's Seminary internal road, Tharakkulam Chanel lane, Martin Road East Lane, Madam Road East Lane, Rasavin thoddam Lane | 3744508.5 | CF | NCB | RPC | N | Completed | 2019.05.24 | 2019.08.17
16 | Renovation of Sandanamatha 2nd Lane, Sandanamatha -Kachcheri Nallur Connection (Columbothurai Connection) road, Kattukanthor Lane, Racca Lane, Temple Road By Lane. | 3727638.5 | CF | NCB | RPC | N | Completed | 2019.05.24 | 2019.08.17
17 | Renovation of Rakka Lane 2, Racca Lane -1, Stanley Road 1st Lane, Stanley Road 2 nd Lane, Sirambiyady Lane, Sirambiyady Lane, Kannathitty Cross Lane | 4129999 | CF | NCB | RPC | N | Completed | 2019.05.24 | 2019.08.17
18 | Renovation of Arevolee 1st lane, Senivasakam cross lane, Solapuram lanes, Villundi Cemetry road, Kannathitty Lane, C Ponnambalam Lane off Stanley Road, Karainagar Cross Road, Muslim College Road By Lane 1 | 4098442.4 | CF | NCB | RPC | N | Completed | 2019.05.24 | 2019.08.17
19 | Renovation of Concrete road at Water tank 6th cross lane, Gurunagar 2nd cross lane, New beach road Ice plant road link road, Concrete road at beach road by lane 1, Concrete road at beach road by lane 2. | 4571758.79 | CF | NCB | RPC | N | Completed | 2019.06.19 | 2019.08.27
20 | Renovation of Arul madha (church ) Kovil road, Raalvady lane (1,2 and 3 lane), Thillai vayal lane, Mathyoos cross road hand rail work at Chundukuli,Bishop house internal road, Thodarpakam internal road. | 4731050.56 | CF | NCB | RPC | N | Completed | 2019.06.19 | 2019.08.27
21 | Renovation of Safi nagar main road, Amman road at Nawanthurai, Nawanthurai library road, St’Marys road, St’Marys new road, Safi Nagar (1st, 2nd 3rd ) lane. | 4414643.18 | CF | NCB | RPC | N | Completed | 2019.06.19 | 2019.08.27
22 | Renovation of Drainage at ward 27, new sea road and new park road channel. | 1129605.5 | CF | NCB | RPC | N | Completed | 2019.08.13 | 2019.09.25
23 | Improvement of Navalar road 2nd lane, Meenadchi amman road stage I and Meenadchi amman road stage II. | 1959428.81 | CF | NCB | RPC | N | Completed | 2019.09.27 | 2019.10.30
24 | Renovation of Drainage at ward 26, water tank road, 6th cross lane. | 1148113.89 | CF | SHOPING | RPC | N | Completed | 2019.08.09 | 2019.10.25
25 | Renovation of Sinnakkadai road bridge, Central east road 1st cross and 2nd cross bridges (Drain Aqueduct), Koyathoddam new road small bridges. | 1287984 | CF | SHOPING | RPC | N | Completed | 2019.08.09 | 2019.09.25
26 | Renovation of Navalar road by lane 1, Navalar road by lane 3, Colombuthurai 2nd lane, Muslim college road by lane 2. | 1785741 | CF | SHOPING | RPC | N | Completed | 2019.10.09 | 2019.09.25
27 | Renovation of Temple road by lanes (03 Nos) Property valuer lane, Tasan farm lane and In front of former chief minister home lane. | 1277667 | CF | SHOPING | RPC | N | Completed | 2019.08.09 | 2019.09.25
28 | Renovation of New housing project road - Reclamation Kurunagar and Eachamooddai Beach road sub lane. | 1604191.4 | CF | SHOPING | RPC | N | Completed | 2019.09.02 | 2019.09.25
29 | Renovation of St.Peters lane - Opposite OLR Church, Hospital road, Ramaiya Chettiyar Lane and Rasavinthoddam lane (Bar lane). | 1393092.5 | CF | SHOPING | RPC | N | Completed | 2019.09.02 | 2019.09.25
30 | Renovation of Pulanthy lane, Yal vempadi high school internal road, and Navanthurai 1st sub lane. | 1601467.5 | CF | SHOPING | RPC | N | Completed | 2019.09.02 | 2019.09.25
31 | Renovation of Water Tank 2nd Cross, David Road - Sebestian Street sub lane, Kondaddy Road – Kurunagar and Mountcarmel sub lane, Gurunagar west. | 2016856.78 | CF | SHOPING | RPC | N | Completed | 2019.09.02 | 2019.09.25
32 | Renovation of Vellantheru Veethy, Mohideen Mosque lane, Moor street, Seliyan 1st lanes and Kaamaal lane. | 1523997 | CF | SHOPING | RPC | N | Completed | 2019.09.02 | 2019.09.25
33 | Renovation of opposite lane to the - Maha vishnu lane- Navalar Road by lane, Pasaiyoor Netmending building approach road. | 1928420 | CF | SHOPING | RPC | N | Completed | 2019.09.27 | 2019.10.25
34 | Renovation of metaling & Tarring part way passiyoor beach road | 1321119.5 | CF | SHOPING | RPC | N | Completed | 2019.09.27 | 2019.10.25
35 | Renovation of Palam Road 4th cross lane Arukalmadam, Kathiappupakar connection to mavadi vellantheru end | 1423185.8 | CF | SHOPING | RPC | N | Completed | 2019.09.27 | 2019.10.25
36 | Renovation of Kelan Road, Koiyathoddam new road sub lane (Concrete road) | 1326379 | CF | SHOPING | RPC | N | Completed | 2019.09.04 | 2019.10.25
37 | Renovation of Old Park Road By Lane (Near Ds Office) And Jaffna Ds Office Internal Road | 1616561.1 | CF | SHOPING | RPC | N | Completed | 2019.09.04 | 2019.10.25
38 | Renovation of Helen thoddam main road 2nd by lane ( Helenthoddam west side No 557/31) | 1153550 | CF | SHOPING | RPC | N | Completed | 2019.09.04 | 2019.09.25
39 | Renovation of Vidance Road - stage 1 at Eachamoddai | 1095095.75 | CF | SHOPING | RPC | N | Completed | 2019.09.04 | 2019.09.25
40 | Renovation of Vidance Road - stage 2 at Eachamoddai | 1102794 | CF | SHOPING | RPC | N | Completed | 2019.09.04 | 2019.09.25
41 | Renovation of Mudalikulam road at Eachchamoddai – stage 1 and stage 2 | 1956583.2 | CF | SHOPING | RPC | N | Completed | 2019.09.04 | 2019.09.25
42 | Renovation of Kachcheri Nallur by lane and Vidance lane opposite Road | 1385890 | CF | SHOPING | RPC | N | Completed | 2019.09.04 | 2019.09.25
43 | Renovation of Vasanthapuram 1st cross - stage I. | 1477880 | CF | SHOPING | RPC | N | Completed | 2019.09.04 | 2019.10.25
44 | Renovation of Vasanthapuram 1st cross - stage II and Vasanthapuram 1st cross, 4th cross & vasanthapuram 3rd cross lane | 2046562 | CF | SHOPING | RPC | N | Completed | 2019.09.27 | 2019.10.25
45 | Renovation of Vasanthapuram cross road & 3rd cross lane | 1650000 | CF | SHOPING | RPC | N | Completed | 2019.09.27 | 2019.10.25
46 | Construction of interlock paving at old park road ( infront of ds office Jaffna) and interlock paving at old park road ( infront of ds office Jaffna) & st. Johns college Jaffna. | 1827747.5 | CF | SHOPING | RPC | N | Completed | 2019.10.01 | 2019.10.25
47 | Renovation of Mathews road Thiyogu lane, Guruso road right side sub lane, Moris lane, Main street sub lane (main street boc closer road). | 1814746 | CF | SHOPING | RPC | N | Completed | 2019.09.27 | 2019.10.25
48 | Renovation of Kanthar maniyam lane, Rasavinthoddam sub lane and 1st & 2nd cross, Nawanthurai. | 2070737.68 | CF | SHOPING | RPC | N | Completed | 2019.09.27 | 2019.10.25
49 | Renovation of Vithanayar sub lane, Koiyathoddam new road by lane 1, dilan road by lane 1 concreate road and beach road by lane 1. | 1961096.59 | CF | SHOPING | RPC | N | Completed | 2019.10.01 | 2019.10.25
50 | Renovation of Rasavinthoddam Lane (Bar Lane) Stage 2 And Kaddukanthor Road Vairavar Kovil Lane At Chundukuli | 1397356.6 | CF | SHOPING | RPC | N | Completed | 2019.10.07 | 2019.10.25
51 | Renovation of Columbuthurai 4th Cross Road (Near Amman Kovil) | 1799310 | CF | SHOPING | RPC | N | Completed | 2019.10.07 | 2019.10.25
52 | Renovation of Nedunkuylam Pillaiyar Cross Road And Elanthaikula Cross Road (concrete road) | 1789620.16 | CF | SHOPING | RPC | N | Completed | 2019.10.07 | 2019.10.25
53 | Renovation of PointPedro Road 1st Cross Stage 2 And Kelanthodam 1st Cross Road By Lane | 1271981.2 | CF | SHOPING | RPC | N | Completed | 2019.11.05 | 2019.11.25
54 | Renovation of Koiyathoddam New Road By Lane 3 and Vepulananthar veethy lane 1,2 | 1660420.2 | CF | SHOPING | RPC | N | Completed | 2019.10.07 | 2019.11.25
55 | Renovation of Kandy Road (Press Road) Nedukkulam 1st Lane Old Park 1st Lane and Kandy Road Cross Road | 1005426.49 | CF | SHOPING | RPC | N | Completed | 2019.11.10 | 2019.11.25
56 | Renovation of Patkulam 3rd Lane, Patkulam 2nd Lane (Balance Work) and Kachcheri Nallur Sub Lane | 1550478.42 | CF | SHOPING | RPC | N | Completed | 2019.11.10 | 2019.11.25
57 | Renovation of Koiyathoddam New Road By Lane 4, Koiyathoddam New Road By Lane 2 and New Beach Concrete Road Reclamation | 1425165.64 | CF | SHOPING | RPC | N | Completed | 2019.10.01 | 2019.10.25
58 | Renovation of Catechetical Center Internal Road Balance Work, Frost Lane Sub Lane (Frosat) And Patkulam 4th Lane | 1296990 | CF | SHOPING | RPC | N | Completed | 2019.11.10 | 2019.11.25
59 | Construction of interlock paving at old park road ( In front of Ds Office Jaffna ) and Jaffna DS Office to St.Johns College Jaffna – Stage III | 1538394.89 | CF | SHOPING | RPC | N | Completed | 2019.10.10 | 2019.10.28
60 | Construction of interlock paving at in front of St.Johns College, Jaffna – Stage IV | 1631218.96 | CF | SHOPING | RPC | N | Completed | 2019.10.10 | 2019.10.28
61 | Construction of interlock paving at St.Johns College side – Stage V | 1651648.81 | CF | SHOPING | RPC | N | Completed | 2019.10.10 | 2019.10.28
62 | Construction of interlock paving at old park road ( in front of DS Office Jaffna ) and Jaffna DS Office to St.Johns College to Bastian Junction, Jaffna – Stage VI | 1660532.46 | CF | SHOPING | RPC | N | Completed | 2019.10.10 | 2019.10.28
63 | Construction of interlock paving at A9 road near old park – Stage VII | 1660532.46 | CF | SHOPING | RPC | N | Completed | 2019.10.10 | 2019.10.28
64 | Improvement of access arrangements at pannai beach park, Jaffna - Phase I | 1460390 | CF | SHOPING | RPC | N | Completed | 2019.11.10 | 2019.11.25
65 | Improvement of access arrangements at pannai beach park, Jaffna - Phase I - Phase II | 1460390 | CF | SHOPING | RPC | N | Completed | 2019.11.10 | 2019.11.25
66 | Renovation of vasanthapuram 1st cross (Balance work) Stage II | 675565 | CF | SHOPING | RPC | N | Completed | 2019.11.10 | 2019.11.25
67 | Renovation of vasanthapuram 3rd cross road, 3rd cross by lane eachamoddai, Valanpuram 9th cross road balance work and madam road east- balance work | 1591720 | CF | Community based procurement | RPC | N | Completed | 2019.09.04 | 2019.10.25
68 | Renovation of Arulmatha veethy, Kannapuram 3rd lane, Av road sub lane, St.mary new road, bishop house internal road,St.martin's seminary internal road and navanthurai beach road balance work | 1653678.83 | CF | Community based procurement | RPC | N | Completed | 2019.09.19 | 2019.10.25
69 | Renovation of Catechetical centre internal road & st. Antaneys' by lane pasaiyor, Rajasingam cross road & solaman cross road and Sebastiyan by road 3rd cross, beach road cross at pasaiyor | 1293534.7 | CF | Community based procurement | RPC | N | Completed | 2019.09.25 | 2019.10.25
70 | Renovation of pasaiyor 1st cross lane, Elders home amala utpavam internal road, Beach road near holy cross and 3rd cross road front lane pasaiyor | 1959316.2 | CF | Community based procurement | RPC | N | Completed | 2019.09.25 | 2019.10.25
71 | Renovation of Navalar road by lane 1( concrete road) and navalar road by lane 3 ( concrete road) | 810219.75 | CF | Community based procurement | RPC | N | Completed | 2019.10.01 | 2019.11.30
72 | Renovation of Pasaiyor ground by lane, Columbagam cross road (near church lane) and Swamiyar road by lane (vasanthagam) | 1306959.45 | CF | Community based procurement | RPC | N | Completed | 2019.10.01 | 2019.11.30
73 | Renovation of pasaiyor beach cross road 1st, 2nd and kevy by road | 1046235.83 | CF | Community based procurement | RPC | N | Completed | 2019.10.01 | 2019.11.30
74 | Renovation of Holy cross convent internal road, Holy cross hospital internal road, Main street 1st cross and Lourdes convent internal road | 1543667.2 | CF | Community based procurement | RPC | N | Completed | 2019.10.04 | 2019.11.30
75 | Incurred for the beach pavement at Pasaiyoor, Jaffna. | 1993949.35 | CF | Community based procurement | RPC | N | Completed | 2019.10.01 | 2019.11.30
76 | Improvement of opposite lane to the mahavishnu lane navalar road by lane and reconstruction of ward-21,Mathews road 2nd lane drainage canal work. | 750220.55 | CF | Community based procurement | RPC | N | Completed | 2019.10.30 | 2019.11.30
77 | Central college access | 399640 | CF | Community based procurement | RPC | N | Completed | 2019.11.05 | 2019.11.30
78 | Renovation of Alupanthy fisheries access road | 1411350 | CF | Community based procurement | RPC | N | Completed | 2019.11.05 | 2019.11.30
79 | Improvement of Gurunagar fisheries village internal road stage I | 1658432.57 | CF | Community based procurement | RPC | N | Completed | 2019.11.18 | 2019.11.30
80 | Improvement of Gurunagar fisheries village internal road stage II | 1648836 | CF | Community based procurement | RPC | N | Completed | 2019.11.18 | 2019.11.30
81 | Renovation of Alupanthy Jetty fisheries Access II. | 577081.6 | CF | Community based procurement | RPC | N | Completed | 2019.11.18 | 2019.11.30
82 | Renovation of holy family convent access at Jaffna | 970000 | CF | Community based procurement | RPC | N | Completed | 2019.11.01 | 2019.11.30

## Temples
Revised Proposed Procurement Plan(PPP) - 2019
Dept:-Divisional Secretariat-Jaffna
Department Line Agency / Ministry | Type Of Procurement (Goods, Works,Equipment & Service etc,) | Estimated Cost (Rs.Mn) | Source of Financing Name of the Donor | Procurement method (ICB,NCB)AND Shopping Procedure etc) | Level of authority(CAPC,MPC,DPC,PPC,etc.) | Priority Status U= Urgent P= Priority N=Normal | Current Status of Procurement Preparedness activities | Scheduled date of commencement | Scheduled date of completion | Remarks
Gamperaliya (104-2-6-20-2506)
woks (Temples)
1 | Renovation of Arulmihu Sri Gnanavairavar Temple (at Etchamoddai) | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.06 | 2019.08.30
2 | Renovation of Renovation of Puthumai MadhaChurch | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.06 | 2019.08.30
3 | Renovation of Arulmihu Sri Gnanavairavar Temple (at BA Thamby Lane) | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.08 | 2019.08.30
4 | Renovation of Punitha Tresha Church (at Maruthady) | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.08 | 2019.08.30
5 | Renovation of Sri Chandirasegara Pillayar Kovil - Columbuthurai | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.08 | 2019.08.30
6 | Renovation of Sri Angusapasa Keeripillayar Kovil | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.08 | 2019.08.30
7 | Renovation of Sri Nagnaviravar Sri Meenadchiyampal temple, Sinnakkadai | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.08 | 2019.08.30
8 | Renovation of Punitha Annai Kovil (at Pandiyanthalvu, Colombuthurai) | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.08 | 2019.08.30
9 | Renovation of Arasady Vairavar Kovil (at Arukalmadam) | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.24 | 2019.08.30
10 | Renovation of Arulmihu Sri Gnana Vairavar kovil- Moolai Road, Chundikuli | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.06 | 2019.09.30
11 | Renovation of Vannai Sri Mahamari AmmanTemple (at Kilnner Lane) | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.07 | 2019.09.30
12 | Renovation of 5th Floor Karththar Church | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.07 | 2019.09.30
13 | Renovation of Katphaka Pillaiyar Kovil (at Maruthady) | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.07 | 2019.09.30
14 | Renovation of Sebasthiyar Church | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.07 | 2019.09.30
15 | Renovation of Mohideen Jumma Mosque (at Five Junction, Moor Street) | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.21 | 2019.09.30
16 | Renovation of Sri Vatharipeeda Vinayagar Temple | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.21 | 2019.09.30
17 | Renovation of Sri Ampalavannar Vinayagar Kovil (at Nedugulam) | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.21 | 2019.09.30
18 | Renovation of Arul Atchiramam KulanthaiYesu Church | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.05 | 2019.10.30
19 | Renovation of Punitha Lurdhu Anai Kebi Church | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.10 | 2019.10.30
20 | Renovation of Sri Gnanavairavar Temple , Puthiyakudiyiruppu,Araly Road | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.11 | 2019.10.30
21 | Renovation of Kolai Vilakki Madha Church | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.06 | 2019.09.30
22 | Renovation of Vairavar Kovil - Rakka Lane | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.10 | 2019.10.30
23 | Renovation of Sinnappalivasal (at Muslim College Road) | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.05 | 2019.10.30
24 | Renovation of Masjid Maryam- Muslim college Road, Jaffna | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.29 | 2019.10.30
25 | Renovation of Gnanselva Vinayagar Kovil (at Koyathoddam) | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.05 | 2019.10.30
26 | Renovation of st.James Church - Gurunagar | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.29 | 2019.10.30
27 | Renovation of Parisuththa Karmel Madha Church | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.21 | 2019.09.30
28 | Renovation of Koddady Arulmihu Srignanavairavar Temple | 485000 | CF | Community Based Procument |  | N | Completed | 2019.10.01 | 2019.11.30
29 | Renovation of Koddady Muneswaran Temple | 485000 | CF | Community Based Procument |  | N | Completed | 2019.10.01 | 2019.11.30
30 | Renovation of Santhayarmadam Srikatpaga Vinayagar Temple | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
31 | Renovation of Station Road Aladi Vinayagar Temple | 485000 | CF | Community Based Procument |  | N | Completed | 2019.09.26 | 2019.11.30
32 | Renovation of Gnanavairavar Temple - J/84 | 485000 | CF | Community Based Procument |  | N | Completed | 16.08.2019 | 2019.11.30
33 | Sri Gnanavairavar Temple PuthiyakudiruppuAraly Road | 485000 | CF | Community Based Procument |  | N | Completed | 2019.09.03 | 2019.11.30
34 | Renovation of Aththiyadi Sithambaranadaraya Veerakaththi Vinayagar Temple | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
35 | Renovation of Gnanavairavar Temple - J/65 | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.02 | 2019.11.30
36 | Renovation of Villunri Veerakaththi VinayagarTemple | 485000 | CF | Community Based Procument |  | N | Completed | 2019.10.01 | 2019.11.30
37 | Renovation of Karumariyamman Temple | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
38 | Station Road Aladi Vinayagar Temple | 485000 | CF | Community Based Procument |  | N | Completed | 2019.09.26 | 2019.11.30
39 | Renovation of Kanitti Kaali Kovil | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
40 | Santhaiyar madam Pillayaiyar temple - fort | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
41 | Renovation of KKS Road Mohammadiya Thakkiya | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
42 | Renovation of Aboobakkar Jumma Mosque -Pommaweli | 485000 | CF | Community Based Procument |  | N | Completed | 2019.09.26 | 2019.11.30
43 | Renovation of Kaamaal Mosque - Kaamaal Road, Moor Street | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.02 | 2019.11.30
44 | Renovation of Mohideen Jumma Mosque - Manipay Road | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
45 | Renovation of Semmaderu Mohideen JummaMosque | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
46 | Renovation of St.Marys Cathedral | 485000 | CF | Community Based Procument |  | N | Completed | 2019.10.01 | 2019.11.30
47 | Renovation of St.James Church - Kurunagar | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
48 | Renovation of St.Anony's Church - Pasaiyoor | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
49 | Renovation of St.Juveniyar Church - Hospital Road | 485000 | CF | Community Based Procument |  | N | Completed | 2019.10.01 | 2019.11.30
50 | Renovation of Velankanni Church - Eliloor | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
51 | Renovation of St.Joseph Church - Valanpuram | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
52 | Renovation of Punitha Sebamalai Madha Church -Colombuthurai | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
53 | Renovation of Christhu Arasar Church - Koyyathottam | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
54 | Renovation of Adaikala Annai Church | 485000 | CF | Community Based Procument |  | N | Completed | 2019.10.01 | 2019.11.30
55 | Renovation of St. Nicholas Church | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
56 | Renovation of St. Yagappar Church - Vasanthapuram | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.02 | 2019.11.30
57 | Renovation of St. Mary's Church - Navanthurai | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.16 | 2019.11.30
58 | Muneeswaran Temple -Fort | 485000 | CF | Community Based Procument |  | N | Completed | 2019.10.01 | 2019.11.30
59 | Velankanni Church - Beach Road | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.02 | 2019.11.30
60 | Aarokkiyanadhar temple - St.Rock | 485000 | CF | Community Based Procument |  | N | Completed | 2019.10.01 | 2019.11.30
61 | Renovation of St.John's Church - Main Street | 485000 | CF | Community Based Procument |  | N | Completed | 2019.09.03 | 2019.11.30
62 | Renovation of St. Mary's Cemetery Church | 485000 | CF | Community Based Procument |  | N | Completed | 2019.09.26 | 2019.11.30
63 | Renovation of Methodist Church Sri Lanka Jaffna Curcuit - Vembady Road | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.02 | 2019.11.30
64 | Renovation of Infant Church - Kulanthaiyesu - Jaffna town east | 485000 | CF | Community Based Procument |  | N | Completed | 2019.08.02 | 2019.11.30

## Sanitary
Revised Proposed Procurement Plan(PPP) - 2019
Dept:-Divisional Secretariat-Jaffna
Department Line Agency / Ministry | Type Of Procurement (Goods, Works,Equipment & Service etc,) | Estimated Cost (Rs.Mn) | Source of Financing Name of the Donor | Procurement method (ICB,NCB)AND Shopping Procedure etc) | Level of authority(CAPC,MPC,DPC,PPC,etc.) | Priority Status U= Urgent P= Priority N=Normal | Current Status of Procurement Preparedness activities | Scheduled date of commencement | Scheduled date of completion | Remarks
Gamperaliya (104-2-6-20-2506)
Works ( Sanitory)
1 | J/Central College | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.08.02 | 2019.11.30
2 | J/Katheeja Ladies College | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.08.02 | 2019.11.30
3 | J/Chundikuli Girl's School | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.08.16 | 2019.11.30
4 | J/Holy Family Convent | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.08.16 | 2019.11.30
5 | J/Vaitheswara College | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.08.16 | 2019.11.30
6 | J/Osmaniya College | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.08.16 | 2019.11.30
7 | J/Colombuthurai Hindu Maha Vidyalaya | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.03 | 2019.11.30
8 | J/Pasaiyoor St.Antony's Girls School | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.03 | 2019.11.30
9 | J/St. Rock's Vidyalaya | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.03 | 2019.11.30
10 | J/St. Patrick's College | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.03 | 2019.11.30
11 | J/St. John's College | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.03 | 2019.11.30
12 | J/St. Bosco Vidyalaya | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.03 | 2019.11.30
13 | J/Vembadi Girls College | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.03 | 2019.11.30
14 | J/Colombuthurai St.Joseph Vidyalaya | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16 | 2019.11.30
15 | J/Colombagam Thriyappa Vidyalayam | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16 | 2019.11.30
16 | J/St. Jame's Boys School | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16 | 2019.11.30
17 | J/St. Jame's Girls School | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.03 | 2019.11.30
18 | J/Koddady Namasivaya Vidyalaya | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16 | 2019.11.30
19 | J/Vannai Nvalar Maha Vidyalayam | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16 | 2019.11.30

## park
Revised Proposed Procurement Plan(PPP) - 2019
Dept:-Divisional Secretariat-Jaffna
Department Line Agency / Ministry | Type Of Procurement (Goods, Works,Equipment & Service etc,) | Estimated Cost (Rs.Mn) | Source of Financing Name of the Donor | Procurement method (ICB,NCB)AND Shopping Procedure etc) | Level of authority(CAPC,MPC,DPC,PPC,etc.) | Priority Status U= Urgent P= Priority N=Normal | Current Status of Procurement Preparedness activities | Scheduled date of commencement | Scheduled date of completion | Remarks
Gamperaliya (104-2-6-20-2506)
Works (Park)
1 | Development of Koyathoddam Pre School Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.08 | 2019.07.08
2 | Development of Arivoly Pre School Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.29 | 2019.08.31
3 | Development of Echchamoddai Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.11 | 2019.08.31
4 | Development of Kalaivani Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.07 | 2019.08.06
5 | Development of St.Nickalas Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.07 | 2019.08.07
6 | Development of St.Mary's Children Park | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.08 | 2019.08.08
7 | Development of St.Roack's Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.20 | 2019.09.20
8 | Development of Gurunagar Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.10 | 2019.08.09
9 | Development of St.Joseph's Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.05 | 2019.07.05
10 | Development of Barathy Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.13 | 2019.08.13
11 | Development of Eliloor Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.05 | 2019.09.06
12 | Development of St Mary's Vidyalayam Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.26 | 2019.11.30
13 | Development of Apostalic Carmel Pre School Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.08 | 2019.07.08
14 | Development of Thodarmady Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.08 | 2019.07.26
15 | Development of Subramaniyam Children Park | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.17 | 2019.09.17
16 | Development of Jetliners Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.08 | 2019.07.08
17 | Sri vikneswara viddiyalayam Children Park | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.10 | 2019.09.31
18 | Development of Vasanthapuram Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16 | 2019.11.30
19 | Development ofSt Antony's Girls School Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16 | 2019.11.30
20 | Development of St palar Pagal parararippunilayam Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.26 | 2019.11.30
21 | Development of Al-Ashar preschool Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16 | 2019.11.30
22 | Development of Green field children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.08.02 | 2019.09.31
23 | Development of Chelvanayakam square children Park | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.03 | 2019.10.30
25 | Development of St.Roack's Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16 | 2019.11.30
26 | Vasanthapuram Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.10.16 | 2019.11.30
27 | Development of Barathy Children Park | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16 | 2019.11.30
28 | Development of Chelvanayakam square children Park | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.10.16 | 2019.11.30

## playground
Revised Proposed Procurement Plan(PPP) - 2019
Dept:-Divisional Secretariat-Jaffna
Department Line Agency / Ministry | Type Of Procurement (Goods, Works,Equipment & Service etc,) | Estimated Cost (Rs.Mn) | Source of Financing Name of the Donor | Procurement method (ICB,NCB)AND Shopping Procedure etc) | Level of authority(CAPC,MPC,DPC,PPC,etc.) | Priority Status U= Urgent P= Priority N=Normal | Current Status of Procurement Preparedness activities | Scheduled date of commencement | Scheduled date of completion | Remarks
Gamperaliya (104-2-6-20-2506)
Works ( Sanitary)
1 | Renovation of Kalaivani Playground - Navanthurai | 970000 | CF | NCB | RPC | N | Completed | 2019.06.06 | 2019.08.06
2 | Renovation of the Echchamoddai Playground - Echchamoddai | 970000 | CF | NCB | RPC | N | Completed | 2019.05.07 | 2019.07.26
3 | Renovation of St.Antony's Playground - Pasaiyoor | 1940000 | CF | NCB | RPC | N | Completed | 2019.05.14 | 2019.07.30
4 | Renovation of St.James Playground - Gurunagar | 1940000 | CF | NCB | RPC | N | Completed | 2019.06.13 | 2019.08.06
5 | Renovation of St.Nickalas Playground - Navanthurai | 970000 | CF | NCB | RPC | N | Completed | 2019.06.06 | 2019.07.31
6 | Renovation of St.Mary's Playground - Navanthurai | 1940000 | CF | NCB | RPC | N | Completed | 2019.06.24 | 2019.08.20
7 | Renovation of St.Roack Playground - Gurunagar | 970000 | CF | NCB | RPC | N | Completed | 2019.05.07 | 2019.08.30
8 | Renovation of Thodarmady Playground - Gurunagar | 970000 | CF | NCB | RPC | N | Completed | 2019.06.06 | 2019.08.06
9 | Renovation of Holy Family Convent Playground | 970000 | CF | NCB | RPC | N | Completed | 2019.07.30 | 2019.08.20
10 | Renovation of J/St.Joseph Mahavidyalaya Playground | 970000 | CF | NCB | RPC | N | Completed | 2019.07.08 | 2019.08.20
11 | Renovation of Muththamil Playground | 485000 | CF | NCB | RPC | N | Completed | 2019.07.08 | 2019.08.26
12 | Renovation of St.John's Playground | 970000 | CF | NCB | RPC | N | Completed | 2019.09.03 | 2019.11.30
13 | Renovation of Bosco School Playground - Maruthady | 485000 | CF | NCB | RPC | N | Completed | 2019.05.03 | 2019.07.20
14 | Renovation of St.Patrick's College Playground | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.05.15 | 2019.08.06
16 | Renovation of Central College Playground | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.31 | 2019.08.30
17 | Renovation of Old Park Playground | 1940000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.10 | 2019.08.20
18 | Renovation of Vembady Playground | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.07.05 | 2019.09.06
19 | Renovation of Vinmeen Playground - Vasanthapuram | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.06.13 | 2019.08.06
21 | Renovation of Vembady Playground | 679000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.03 | 2019.08.25
22 | Renovation of Eachamoddai Playground | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.03 | 2019.09.30
23 | J/Colombuthurai Hindu Maha Vidyalaya | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.03 | 2019.09.30
25 | St mary's vidyalayam play ground | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.11.01 | 2019.11.30
26 | Thodarmady play ground | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16 | 2019.10.30
27 | Thuraiyappa vidyalayam play ground | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16 | 2019.09.30
28 | J/St. Charles Maha Vidyalaya | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.08.16 | 2019.08.30
29 | J/St. John's College | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.03 | 2019.09.30
30 | J/Vaideyswara College | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.03 | 2019.10.30
31 | J/Osmaniya Muslim College | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16 | 2019.10.30
32 | Besky Community Center Volly ball ground | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.11 | 2019.10.30
33 | Racka road play ground | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.08.10 | 2019.08.30
35 | Meenatchi play ground | 485000 | CF | Community Based Procument | RPC | N | Completed | 2019.08.15 | 2019.08.30
36 | Renovation of Vembady Playground | 291000 | CF | Community Based Procument | RPC | N | Completed | 2019.11.01 | 2019.11.30
37 | Vaitheeswara Playground | 838080 | CF | Community Based Procument | RPC | N | Completed | 2019.09.26 | 2019.10.30

## IDP
Revised Proposed Procurement Plan(PPP) - 2019
Dept:-Divisional Secretariat-Jaffna
Department Line Agency / Ministry | Type Of Procurement (Goods, Works,Equipment & Service etc,) | Estimated Cost (Rs.Mn) | Source of Financing Name of the Donor | Procurement method (ICB,NCB)AND Shopping Procedure etc) | Level of authority(CAPC,MPC,DPC,PPC,etc.) | Priority Status U= Urgent P= Priority N=Normal | Current Status of Procurement Preparedness activities | Scheduled date of commencement | Scheduled date of completion | Remarks
IDP
Works
1 | Reconstruction of Kamal Jumma Mosque | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.08.08 | 2019.1
2 | Reconstruction of Mohideen Thakkiya Mosque | 582000 | CF | Community Based Procument | RPC | N | Completed | 2019.08.08
3 | Providing Electricity Connection and Lighting to St.mary's Ground | 970000 | CF | Community Based Procument | RPC | N | Completed | 2019.08.08
4 | Renovation work of Manfaul Uloom Madrasa Cultural center | 776000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16
5 | Renavation and roofing works for Abubuker Jumma masjid | 1950000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.16
6 | Construction and Renovation Mahmoodia Mosque KKS Road | 1170000 | CF | Community Based Procument | RPC | N | Completed | 2019.09.18
7 | Renovation and furniture for the community centers | 97500 | CF | Community Based Procument | RPC | N | Completed | 2019.10.30
8 | Renovation ,buying equpments and furnitures for pre school | 243750 | CF | Community Based Procument | RPC | N | Completed | 2019.11.08
9 |  |  | CF | Community Based Procument | RPC | N | Completed
10 |  |  | CF | Community Based Procument | RPC | N | Completed
11 |  |  | CF | Community Based Procument | RPC | N | Completed
12 |  |  | CF | Community Based Procument | RPC | N | Completed
13 |  |  | CF | Community Based Procument | RPC | N | Completed
14 |  |  | CF | Community Based Procument | RPC | N | Completed
16 |  |  | CF | Community Based Procument | RPC | N | Completed
17 |  |  | CF | Community Based Procument | RPC | N | Completed
18 |  |  | CF | Community Based Procument | RPC | N | Completed
19 |  |  | CF | Community Based Procument | RPC | N | Completed
21 |  |  | CF | Community Based Procument | RPC | N | Completed
22 |  |  | CF | Community Based Procument | RPC | N | Completed
23 |  |  | CF | Community Based Procument | RPC | N | Completed
25 |  |  | CF | Community Based Procument | RPC | N | Completed
26 |  |  | CF | Community Based Procument | RPC | N | Completed
27 |  |  | CF | Community Based Procument | RPC | N | Completed
28 |  |  | CF | Community Based Procument | RPC | N | Completed
29 |  |  | CF | Community Based Procument | RPC | N | Completed
30 |  |  | CF | Community Based Procument | RPC | N | Completed
31 |  |  | CF | Community Based Procument | RPC | N | Completed
32 |  |  | CF | Community Based Procument | RPC | N | Completed
33 |  |  | CF | Community Based Procument | RPC | N | Completed
35 |  |  | CF | Community Based Procument | RPC | N | Completed
36 |  |  | CF | Community Based Procument | RPC | N | Completed
37 |  |  | CF | Community Based Procument | RPC | N | Completed

## Sheet2 (2)
Revised Proposed Procurement Plan(PPP) - 2019
Dept:-Divisional Secretariat-Jaffna
Department Line Agency / Ministry | Type Of Procurement (Goods, Works,Equipment & Service etc,) | Estimated Cost (Rs.Mn) | Source of Financing Name of the Donor | Procurement method (ICB,NCB)AND Shopping Procedure etc) | Level of authority(CAPC,MPC,DPC,PPC,etc.) | Priority Status U= Urgent P= Priority N=Normal | Current Status of Procurement Preparedness activities | Scheduled date of commencement | Scheduled date of completion | Remarks
Deparment Of Nationa Budjet | woks
1 | Renovation of Vannai Sri Mahamari AmmanTemple (at Kilnner Lane) | 485000 | CF | Community Base Procument | RPC | U | Completed | 07.06.2019
2 | Renovation of Arulmihu Sri Gnanavairavar Temple (at BA Thamby Lane) | 485000 | CF | Community Base Procument | RPC | U | Completed | 08.05.2019
3 | Renovation of Kolai Vilakki Madha Church | 485000 | CF | Community Base Procument | RPC | U | Completed
5 | Renovation of Arulmihu Sri Gnana Vairavar kovil- Moolai Road, Chundikuli | 485000 | CF | Community Base Procument | RPC | U | Completed | 06.06.2019
6 | Renovation of Punitha Tresha Church (at Maruthady) | 485000 | CF | Community Base Procument | RPC | U | Completed | 08.05.2019
7 | Renovation of Vairavar Kovil - Rakka Lane | 485000 | CF | Community Base Procument | RPC | U | Completed
8 | Renovation of Katphaka Pillaiyar Kovil (at Maruthady) | 485000 | CF | Community Base Procument | RPC | U | Completed | 07.06.2019
9 | Renovation of Arul Atchiramam Kulanthai Yesu Church | 485000 | CF | Community Base Procument | RPC | U | Completed | 05.07.2019
10 | Renovation of Arulmihu Sri Gnanavairavar Temple (at Etchamoddai) | 485000 | CF | Community Base Procument | RPC | U | Completed | 06.05.2019
12 | Renovation of Sri Gnanavairavar Temple , Puthiyakudiyiruppu,Araly Road | 485000 | CF | Community Base Procument | RPC | U | Completed | 11.07.2019
13 | Renovation of Arasady Vairavar Kovil (at Arukalmadam) | 485000 | CF | Community Base Procument | RPC | U | Completed | 24.05.2019
14 | Renovation of Punitha Lurdhu Anai Kebi Church | 485000 | CF | Community Base Procument | RPC | U | Completed | 10.07.2019
15 | Renovation of Sinnappalivasal (at Muslim College Road) | 485000 | CF | Community Base Procument | RPC | U | Completed
16 | Renovation of Mohideen Jumma Mosque (at Five Junction, Moor Street) | 485000 | CF | Community Base Procument | RPC | U | Completed | 07.06.2019
17 | Renovation of Masjid Maryam- Muslim college Road, Jaffna | 485000 | CF | Community Base Procument | RPC | U | Completed
18 | Renovation of Gnanselva Vinayagar Kovil (at Koyathoddam) | 485000 | CF | Community Base Procument | RPC | U | Completed
19 | Renovation of st.James Church - Gurunagar | 485000 | CF | Community Base Procument | RPC | U | Completed
20 | Renovation of Parisuththa Karmel Madha Church | 485000 | CF | Community Base Procument | RPC | U | Completed
21 | Renovation of Sri Ampalavannar Vinayagar Kovil (at Nedugulam) | 485000 | CF | Community Base Procument | RPC | U | Completed | 08.06.2019
22 |  | 485000 | CF | Community Base Procument | RPC | U | Completed | 06.05.2019
23 | Renovation of Sri Vatharipeeda Vinayagar Temple | 485000 | CF | Community Base Procument | RPC | U | Completed | 07.06.2019
26 | Renovation of Sri Chandirasegara Pillayar Kovil - Columbuthurai | 485000 | CF | Community Base Procument | RPC | U | Completed | 08.05.2019
27 | Renovation of Sri Angusapasa Keeripillayar Kovil | 485000 | CF | Community Base Procument | RPC | U | Completed | 08.05.2019
28 | Renovation of Sri Nagnaviravar Sri Ambal temple, Sinnakkadai | 485000 | CF | Community Base Procument | RPC | U | Completed | 08.05.2019
29 | Renovation of Vairvar Temple -Nariyankundu ground housing Scheme ( at Racka Road) | 485000 | CF | Community Base Procument | RPC | U | Completed | 08.05.2020
30 | Renovation of Punitha Annai Kovil (at Pandiyanthalvu, Colombuthurai) | 485000 | CF | Community Base Procument | RPC | U | Completed | 08.05.2019

## TEMPLE
|  | Amendment |  | Agreement Amount | Agreement Date | GN Div | Tender /No | Tender Date | Tender Awarding Society | Remarks
1 | Renovation of Sri Mahamari Temple (at Kilnner Lane) | Renovation of Vannai Sri Mahamari AmmanTemple (at Kilnner Lane) | 0.5 | 485000 | 07.06.2019 | J/82 | Y/11 | 06.06.2019 | Vannai Sri Mahamariyamman Temple
2 | Renovation of Gnanavairavar Temple (at BA Thamby Lane) | Renovation of Arulmihu Sri Gnanavairavar Temple (at BA Thamby Lane) | 0.5 | 485000 | 08.05.2019 | J/82 | Y/03 | 06.05.2019 | Vannarpannai Arulmiku Gnanavairavar Alaya Paripalana Sabai
3 | Renovation of Kolai Vilakki Madha Church | Renovation of Kolai Vilakki Madha Church | 0.5 | 485000 |  |  | Y/15
4 | Renovation of 5th Floor Karththar Church |  | 0.5 | 485000 | 07.06.2019 | J/68 | Y/12 | 06.06.2019 | Kurunagar Flats Community Centre
5 | Renovation of Chundukuli Samundi Vairavar Kovil(Arulmihu Sri Gnanavairavar Kovil) | Renovation of Arulmihu Sri Gnana Vairavar kovil- Moolai Road, Chundikuli | 0.5 | 485000 | 06.06.2019 | J/76 | Y/10 | 06.06.2019 | Arulmihu Sri Gnanavairavar Alayam
6 | Renovation of Punitha Tresha Church (at Maruthady) | Renovation of Punitha Tresha Church (at Maruthady) | 0.5 | 485000 | 08.05.2019 | J/77 | Y/04 |  | St.Theresa's Church Nirvagam
7 | Renovation of Pillaiyar Kovil - Rakka Lane | Renovation of Vairavar Kovil - Rakka Lane | 0.5 | 485000 |  |  | Y/23
8 | Renovation of Katphaka Pillaiyar Kovil (at Maruthady) | Renovation of Katphaka Pillaiyar Kovil (at Maruthady) | 0.5 | 485000 | 07.06.2019 | J/77 | Y/14 | 06.06.2019 | Sri Katphaka Vinayagar Alaya Paripalanasabai
9 | Renovation of Arul Atchiramam Kulanthai Yesu Church | Renovation of Arul Atchiramam Kulanthai Yesu Church | 0.5 | 485000 | 05.07.2019 | J/74 | Y/20
10 | Renovation of Gnanavairavar Temple (at Etchamoddai) | Renovation of Arulmihu Sri Gnanavairavar Temple (at Etchamoddai) | 0.5 | 485000 | 06.05.2019 | J/66 | Y/01 | 03.05.2019 | Arulmiku Gnanaviravar thevasthana Paripalana Sabai
11 | Renovation of Sebasthiyar Church | Renovation of Sebasthiyar Church | 0.5 | 485000 | 07.06.2019 | J/70 | Y/13 | 06.06.2019 | St.Sebasthiyar Church - Gurunagar
12 | Renovation of Thamarai Temple | Renovation of Sri Gnanavairavar Temple , Puthiyakudiyiruppu,Araly Road | 0.5 | 485000 | 11.07.2019 |  | Y/25 | 10.07.2019
13 | Renovation of Arasady Vairavar Kovil (at Arukalmadam) | Renovation of Arasady Vairavar Kovil (at Arukalmadam) | 0.5 | 485000 | 24.05.2019 | J/88 | Y/09 | 22.05.2019 | Arasady Sri Gnanaviravar Swamy Thirukkovil |  | 772912477
14 | Renovation of Punitha Lurdhu Anai Kebi Church | Renovation of Punitha Lurdhu Anai Kebi Church | 0.5 | 485000 | 10.07.2019 |  | Y/24 | 10.07.2019 | Christ the king Church
15 | Renovation of Sinnappalivasal (at Muslim College Road) | Renovation of Sinnappalivasal (at Muslim College Road) | 0.5 | 485000 |  |  | Y/21
16 | Renovation of Sinna Mohidden Mosque (at Five Junction, Moor Street) | Renovation of Mohideen Jumma Mosque (at Five Junction, Moor Street) | 0.5 | 485000 | 07.06.2019 | J/87 | Y/19 |  | Sinna Mohidden Mosque (at Five Junction, Moor Street)
17 | Renovation of Tharusalam Mosque (at Tharusalam, Puthiya Kudiyiruppu) | Renovation of Masjid Maryam- Muslim college Road, Jaffna | 0.5 | 485000 |  |  | Y/27 |  | St.Roche's Community Centre | Ten.Sig
18 | Renovation of Gnanavel Vinayagar Kovil (at Koyathoddam) | Renovation of Gnanselva Vinayagar Kovil (at Koyathoddam) | 0.5 | 485000 |  |  | Y/22
19 | Renovation of Sri Pathrakali Amman Kovil (at Ariyalai) | Renovation of st.James Church - Gurunagar | 0.5 | 485000 |  |  | Y/26 |  | st.James Church - Gurunagar | Ten.Sig
20 | Renovation of Parisuththa Karmel Madha Church | Renovation of Parisuththa Karmel Madha Church | 0.5 | 485000 |  | J/71 | Y/16 | 21.06.2019 | Carmel Matha Community Centre
21 | Renovation of Pillaiyar Kovil (at Nedunkulam) | Renovation of Sri Ampalavannar Vinayagar Kovil (at Nedugulam) | 0.5 | 485000 | 08.06.2019 | J/61 | Y/17 | 21.06.2019 | Sri Ambalavana Vinayagar Alayam
22 | Renovation of Renovation of Puthumai Madha Church | Renovation of Renovation of Puthumai Madha Church | 0.5 | 485000 | 06.05.2019 | J/71 | Y/02 | 03.05.2019 | Our Lady of Miracle Church
23 | Renovation of Pillaiyar Kovil (at Ilanthaikulam) | Renovation of Sri Vatharipeeda Vinayagar Temple | 0.5 | 485000 | 07.06.2019 | J/63 | Y/18 | 21.06.2019 | Sri Vathiripeeda Vinayakar Alayam
24 | Renovation of Pillaiyar Kovil (at Uppukulam) (Sri SanthirasekarappillaiyarKovil) | Renovation of Sri Chandirasegara Pillayar Kovil - Columbuthurai | 0.5 | 485000 | 08.05.2019 | J/62 | Y/05 | 06.05.2019 | Sri Santhirasekarappillaiyar Amman Iyanar Vairavar Kovil Nirvakam
25 | Renovation of Keeripillaiyar Kovil (Sri Ankushapasha Keeripillaiyar kovil) | Renovation of Sri Angusapasa Keeripillayar Kovil | 0.5 | 485000 | 08.05.2019 | J/82 | Y/06 | 06.05.2019 | Sri Ankushapasha Keeripillaiyar Thevesthanam
26 | Renovation of Vairavar Kovil (Sri Gnanavairvar Sri Meenadchiyampal Thevasthanam ) | Renovation of Sri Nagnaviravar Sri Ambal temple, Sinnakkadai | 0.5 | 485000 | 08.05.2019 | J/72 | Y/07 | 06.05.2019 | Sri Gnanavairvar Sri Meenadchiyampal Thevasthanam
27 | Renovation of Pillaiyar Kovil (at Maruthady Racka Road) | Renovation of Vairvar Temple -Nariyankundu ground housing Scheme ( at Racka Road) | 0.5 | 485000
28 | Renovation of Punitha Annai Kovil (at Pandiyanthalvu, Colombuthurai) | Renovation of Punitha Annai Kovil (at Pandiyanthalvu, Colombuthurai) | 0.5 | 485000 | 08.05.2019 | J/76 | Y/08 | 06.05.2019 | St.Annes Church ( at Pandiyanthalvu Columbuthurai)