## Sapirigamak
Ref. No. | Description | Estimated Cost (Rs. - Mn.) |  | Procurement Method (ICB, LIB, LNB,NCB &National Shopping etc.) | App. DPC & TEC | Prep. Bidding Documents | App. Bidding Documents by DPC / RPC | Invite Bids | Clarific / Pre. Bid. Confere. | Bid Receive / Bid Opening | Tech. Evaluation | PC Approval | Contract Award | Contract Signed | Complete Works / Goods/ Services delivered | Contract Amount Name of the Contractor | Remarks
| Sapiri Gamak |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Improvement of Elanthaikulam Pillaijar front lane | 508325.05 | S | Community bassed Procurement | 9: 2020.02.12; 10: 2020.02.12; 11: 2020.07.15; 12: Columbuthurai west community centre & Jet liners association
|  |  | A |  | 9: 2020.02.12; 10: 2020.02.20; 11: 2020.06.20
2 | Reconstruction of Ilanthaikulam Inlet canal work. | 1321089.2 | S | Community bassed Procurement | 9: 2020.02.18; 10: 2020.02.19; 11: 2020.07.20; 12: Columbuthurai west community centre & Jet liners association
|  |  | A |  | 9: 2020.02.18; 10: 2020.02.20; 11: 2020.07.20
3 | Improvement of 1,2,3 lane near thodarmadi (concret road). | 1494178.9 | S | Community bassed Procurement | 9: 2020.02.18; 10: 2020.02.19; 11: 2020.05.20; 12: Reclamation east beski WRDS
|  |  | A |  | 9: 2020.02.18; 10: 2020.02.20; 11: 2020.05.15
4 | Reconstruction of new housing scheme canal work of reclamation east. | 253596.59 | S | Community bassed Procurement | 9: 2020.02.18; 10: 2020.02.19; 11: 2020.07.31; 12: Reclamation east beski WRDS
|  |  | A |  | 9: 2020.02.18; 10: 2020.02.20; 11: 2020.07.29
5 | Reconstruction of Kalaippulavar road drainage of sirambiyadi | 417772.95 | S | Community bassed Procurement | 9: 2020.02.18; 10: 2020.02.19; 11: 2020.09.15; 12: Jaffna sirambiyadi WRDS
|  |  | A |  | 9: 2020.02.18; 10: 2020.02.20; 11: 2020.08.18
6 | Reconstruction of Madam road (vempady) drainage canal wall work. | 1438765.54 | S | Community bassed Procurement | 9: 2020.02.18; 10: 2020.02.18; 11: 2020.05.18; 12: Cancled
A
7 | Improvement of Kannapuram 4th lane | 1560273.75 | S | Community bassed Procurement | 9: 2020.02.19; 10: 2020.02.20; 11: 2020.05.20; 12: Kannapuram WRDS
|  |  | A |  | 9: 2020.02.19; 10: 2020.02.20; 11: 2020.05.20
8 | Reconstruction of Eachamooddai to beach road canal work of Eachamoodai | 161665.05 | S | Community bassed Procurement | 9: 2020.02.20; 10: 2020.02.21; 11: 2020.05.25; 12: Kalaichudar community centre
|  |  | A |  | 9: 2020.02.20; 10: 2020.02.24; 11: 2020.05.25
9 | Improvement of Osmania college 1st right side lane 2nd lane left side. | 1300810.26 | S | Community bassed Procurement | 9: 2020.02.19; 10: 2020.02.20; 11: 2020.08.28; 12: Moor street north RDS
|  |  | A |  | 9: 2020.02.20; 10: 2020.02.24; 11: 2020.08.17
10 | Construction of Lively hood development centre building J/81 | 1980000 | S | Community bassed Procurement | 9: 2020.02.24; 10: 2020.02.25; 11: 2020.05.25; 12: Koddai Meenadchi WRDS
|  |  | A |  | 9: 2020.02.24; 10: 2020.02.25; 11: 2020.05.25
11 | Construction of Lively hood development centre building.(J/67) | 1980000 | S | Community bassed Procurement | 9: 2020.02.24; 10: 2020.02.25; 11: 2020.05.25; 12: J/Bharathy community centre
|  |  | A |  | 9: 2020.02.24; 10: 2020.02.25; 11: 2020.05.25
12 | Construction of Lively hood development centre building.(J/76) | 1980000 | S | Community bassed Procurement | 9: 2020.02.24; 10: 2020.02.25; 11: 2020.05.25; 12: Sundikuli North elders society
|  |  | A |  | 9: 2020.02.24; 10: 2020.02.25; 11: 2020.05.25
13 | Construction of Lively hood development centre building.(J/61) | 1980000 | S | Community bassed Procurement | 9: 2020.02.24; 10: 2020.02.25; 11: 2020.11.30; 12: Colombuthurai fishermens Co-operative society ltd
|  |  | A |  | 9: 2020.02.24; 10: 2020.02.24
14 | Construction of Lively hood development centre building.(J/69) | 1980000 | S | Community bassed Procurement | 9: 2020.02.24; 10: 2020.02.25; 11: 2020.05.25; 12: Gurunagar fisheries Development society
|  |  | A |  | 9: 2020.02.24; 10: 2020.02.25; 11: 2020.05.25
15 | Reconstruction of Tharakulam scheme canal,2nd road canal and 5th road canal work of ( J/73), Jaffna town west. | 1844000 | S | Community bassed Procurement | 9: 2020.03.04; 10: 2020.03.05; 11: 2020.11.30; 12: Jaffna town west WRDS
|  |  | A |  | 9: 2020.03.04; 10: 2020.03.05
16 | Reconstruction of Gurunagar west village internal flood canal work of (J/71), Jaffna town west. | 1942747.57 | S | Community bassed Procurement | 9: 2020.03.12; 10: 2020.03.13; 11: 2020.10.30; 12: Gurunagar west -J/71 RDS
|  |  | A |  | 9: 2020.03.12; 10: 2020.03.16; 11: 2020.08.20
17 | Reconstruction of 4th cross street drainage work of (J/72), small bazzar, Jaffna. | 1947431.83 | S | Community bassed Procurement | 9: 2020.03.12; 10: 2020.03.16; 11: 2020.11.30; 12: Small bazaar RDS
|  |  | A |  | 9: 2020.03.12; 10: 2020.03.12
18 | Re construction of Lively hood development centre building.(J/70) | 1980000 | S | Community bassed Procurement | 9: 2020.03.12; 10: 2020.03.13; 11: 2020.06.18; 12: St.Sebastiyar community centre
|  |  | A |  | 9: 2020.03.12; 10: 2020.03.18; 11: 2020.06.18
19 | Renovation of community centre (lively hood development centre )building (J/78) | 1980000 | S | Community bassed Procurement | 9: 2020.03.12; 10: 2020.03.12; 11: 2020.06.18; 12: Ariyakulam forward youth club - reading centre
|  |  | A |  | 9: 2020.03.12; 10: 2020.03.18; 11: 2020.06.18
20 | Construction of Lively hood development centre building.(J/80) | 1980000 | S | Community bassed Procurement | 9: 2020.03.12; 10: 2020.03.13; 11: 2020.06.13; 12: Land Issue
A
21 | Construction of concrete road of P.D lane, College road, Asath lane saudilane by lane Jaffna. | 597016.22 | S | Community bassed Procurement | 9: 2020.03.13; 10: 2020.03.16; 11: 2020.09.10; 12: Moor street north RDS
|  |  | A |  | 9: 2020.03.13; 10: 2020.03.17
22 | Improvement of columbuthurai 1,2,3,4 cross road | 226770.15 | S | Community bassed Procurement | 9: 2020.03.17; 10: 2020.03.18; 11: 2020.06.18; 12: colombuthurai east RDS
|  |  | A |  | 9: 2020.03.17; 10: 2020.03.18; 11: 2020.06.18
23 | Reconstruction of Valanpuram beach road flood canal work of (J/62), columbuthurai east, Jaffna. | 1717618.76 | S | Community bassed Procurement | 9: 2020.03.17; 10: 2020.03.18; 11: 2020.10.14; 12: colombuthurai east RDS
|  |  | A |  | 9: 2020.03.17; 10: 2020.03.18
24 | Construction of boundry chailink fence at Kartkulam, Koddady, Jaffna.(J/83) | 1599991.72 | S | Community bassed Procurement | 9: 2020.05.26; 10: 2020.05.27; 11: 2020.08.27; 12: Star community centre
|  |  | A |  | 9: 2020.05.26; 10: 2020.05.27; 11: 2020.08.27
25 | Improvement of Martin lane joint road. | 775136.32 | S | Community bassed Procurement | 9: 2020.06.22; 10: 2020.06.23; 11: 2020.09.23; 12: Jaffna town east elders society
|  |  | A |  | 9: 2020.06.22; 10: 2020.06.23; 11: 2020.07.17
26 | Construction of 13000 Ltr capacity at Pasaiyoor. | 1857939.5 | S | Community bassed Procurement | 9: 2020.06.16; 10: 2020.06.17; 11: 2020.11.30; 12: J/Pasaiyoor St.Antony’s rural fishermen organization
|  |  | A |  | 9: 2020.06.16; 10: 2020.06.18
27 | Sirambiyadi lane drainage | 222517.85 | S | Community bassed Procurement | 9: 2020.06.24; 10: 2020.06.25; 11: 2020.09.28; 12: Jaffna sirambiyadi WRDS
|  |  | A |  | 9: 2020.06.24; 10: 2020.06.25; 11: 2020.08.18
28 | Reconstruction of Vithanayar road sub lane drainage wall work of (J/66), Eachamoddai. | 1407099.77 | S | Community bassed Procurement | 9: 2020.06.25; 10: 2020.06.26; 11: 2020.11.25; 12: Koiyathoddam community centre
|  |  | A |  | 9: 2020.06.25; 10: 2020.06.26
29 | Up grading toilet facilities & necessary to be incurred for J/Nallur vigneswara school | 1980000 | S | Community bassed Procurement | 9: 2020.06.25; 10: 2020.06.26; 11: 2020.09.28; 12: School development committee J/Nallur vigneswara vidyalayam
|  |  | A |  | 9: 2020.06.25; 10: 2020.06.26; 11: 2020.09.28
30 | Renovation of illanthaikulam channel stage II | 115904.8 | S | Community bassed Procurement | 9: 2020.06.26; 10: 2020.06.26; 11: 2020.09.29; 12: Columbuthurai west community centre & Jet liners association
|  |  | A |  | 9: 2020.06.26; 10: 2020.06.29; 11: 2020.08.18
31 | Renovation of Vellantheru drainage | 313882.6 | S | Community bassed Procurement | 9: 2020.06.29; 10: 2020.06.30; 11: 2020.09.30; 12: Jaffna consertium of WRDS
|  |  | A |  | 9: 2020.06.29; 10: 2020.06.30; 11: 2020.07.31
32 | Renovation of Plassas lane culvert | 191000 | S | Community bassed Procurement | 9: 2020.07.01; 10: 2020.07.02; 11: 2020.10.02; 12: Koiyathoddam community centre
|  |  | A |  | 9: 2020.07.01; 10: 2020.07.02; 11: 2020.09.10
33 | Improvement of Mundukkulam | 1934890 | S | Community bassed Procurement | 9: 2020.07.21; 10: 2020.07.22; 11: 2020.10.30; 12: Green field community centre & sports club
|  |  | A |  | 9: 2020.07.21; 10: 2020.07.31
34 | Renovation of lively hood development centre –J/85 | 1980000 | S | Community bassed Procurement | 9: 2020.07.28; 10: 2020.07.29; 11: 2020.10.19; 12: Navanthurai St.Mary’s rural fisheries organization
|  |  | A |  | 9: 2020.07.28; 10: 2020.08.17
35 | Improvement of Vellantheru road work and manipai road pirappamkulam road link road work | 497000 | S | Community bassed Procurement | 9: 2020.08.10; 10: 2020.08.10; 11: 2020.10.19; 12: Geriatrics society vannrpannai – Jaffna
|  |  | A |  | 9: 2020.08.10; 10: 2020.08.17; 11: 2020.09.20
36 | Reconstruction of madam road ( vempady road- J/Holy family convent school front side) drainage canal wall work. | 1200779.31 | S | Community bassed Procurement | 9: 2020.08.10; 10: 2020.08.11; 11: 2020.10.19; 12: Jaffna town east elders society
|  |  | A |  | 9: 2020.08.10; 10: 2020.08.17
37 | Renovation of Katkulam rd | 847000 | S | Community bassed Procurement | 9: 2020.09.25; 10: 2020.09.28; 11: 2020.10.28; 12: Elders society of moor street south Jaffna
|  |  | A |  | 9: 2020.09.25; 10: 2020.09.28
38 | Renovation of Thillaivayal road flood canal culvert | 1980000 | S | Community bassed Procurement | 9: 2020.09.25; 10: 2020.09.28; 11: 2020.10.28; 12: New moor street RDS
|  |  | A |  | 9: 2020.09.25; 10: 2020.09.28
39 | Construction of drinking water purification center | 1980000 | S | Community bassed Procurement | 9: 2020.09.28; 10: 2020.09.29; 11: 2020.10.29; 12: J/pasaiyoor St.Antony's fishermen co-operative society
|  |  | A |  | 9: 2020.09.28; 10: 2020.09.29
40 | Renovation of Pirappankulam Road (Concret Road). | 201000 | S | Community bassed Procurement | 9: 2020.09.28; 10: 2020.09.28; 11: 2020.10.28; 12: Elders Society Vannarpannai
|  |  | A |  | 9: 2020.09.28; 10: 2020.09.28
41 | Kalaipulavar road | 608000 | S | Community bassed Procurement | 9: 2020.10.14; 10: 2020.10.15; 11: 2020.11.16; 12: Jaffna sirambiyadi women rural development society
|  |  | A |  | 9: 2020.10.14; 10: 2020.10.15

## RIDP
Ref. No. | Description | Estimated Cost (Rs. - Mn.) |  | Procurement Method (ICB, LIB, LNB,NCB &National Shopping etc.) | App. DPC & TEC | Prep. Bidding Documents | App. Bidding Documents by DPC / RPC | Invite Bids | Clarific / Pre. Bid. Confere. | Bid Receive / Bid Opening | Tech. Evaluation | PC Approval | Contract Award | Contract Signed | Complete Works / Goods/ Services delivered | Contract Amount Name of the Contractor | Remarks
| RIDP |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of concrete road of Asath lane 2nd cross road | 692781.68 | S | Community bassed Procurement | 9: 2020.02.12; 10: 2020.02.13; 11: 2020.05.14; 12: Moor street north RDS
|  |  | A |  | 9: 2020.02.12; 10: 2020.02.14; 11: 2020.03.11
2 | Improvement of Helanthoddam 4th lane (east side), Jaffna. | 659562.9 | S | Community bassed Procurement | 9: 2020.05.15; 10: 2020.05.18; 11: 2020.07.06; 12: Helanthoddam rural development society
|  |  | A |  | 9: 2020.05.15; 10: 2020.05.20; 11: 2020.07.05
3 | Renovation of Navanthurai south 3rd cross street. | 435445.75 | S | Community bassed Procurement | 9: 2020.05.18; 10: 2020.05.19; 11: 2020.07.07; 12: Navanthurai St.Nicholas rural fisheries organization
|  |  | A |  | 9: 2020.05.18; 10: 2020.05.21; 11: 2020.07.03
4 | Construction of concrete road of new housing road 2nd, 3rd and 4th lanes, Kurunagar. | 922201.29 | S | Community bassed Procurement | 9: 2020.05.20; 10: 2020.05.21; 11: 2020.07.06; 12: Reclamation east beski women rural development society
|  |  | A |  | 9: 2020.05.20; 10: 2020.05.20; 11: 2020.06.12

## others
Ref. No. | Description | Estimated Cost (Rs. - Mn.) |  | Procurement Method (ICB, LIB, LNB,NCB &National Shopping etc.) | App. DPC & TEC | Prep. Bidding Documents | App. Bidding Documents by DPC / RPC | Invite Bids | Clarific / Pre. Bid. Confere. | Bid Receive / Bid Opening | Tech. Evaluation | PC Approval | Contract Award | Contract Signed | Complete Works / Goods/ Services delivered | Contract Amount Name of the Contractor | Remarks
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Constructing cannel and septic tank at Gurunagar market (104-2-14-30-2202/09-04-002)
1 | Construction of drainage at Gurunagar | 1558080 | S | Community bassed Procurement | 9: 2020.07.30; 10: 2020.08.01; 11: 2020.08.31; 12: Gurunagar fishing development society
|  |  | A |  | 9: 2020.07.30; 10: 2020.08.03; 11: 2020.08.31
2 | Construction of PIT and infiltration tank at Gurunagar | 533629.68 | S | Community bassed Procurement | 9: 2020.08.19; 10: 2020.08.19; 11: 2020.08.31; 12: Divisional Federation of Youth Club - Jaffna
|  |  | A |  | 9: 2020.08.19; 10: 2020.08.19; 11: 2020.08.31
Improvements works of the Gurunagar fish landing jetty (405-2-03-64-2509)
1 | Renovation of Jetty at Gurunagar for small boat in Jaffna division | 648295.8 | S | Community bassed Procurement | 9: 2020.10.05; 10: 2020.10.05; 11: 2020.12.31; 12: Gurunagar fishing development society
|  |  | A |  | 9: 2020.10.05; 10: 2020.10.05

## DS office Saprigamak pro.pl (2)
Ref. No. | Description | Estimated Cost (Rs. - Mn.) |  | Procurement Method (ICB, LIB, LNB,NCB &National Shopping etc.) | App. DPC & TEC | Prep. Bidding Documents | App. Bidding Documents by DPC / RPC | Invite Bids | Clarific / Pre. Bid. Confere. | Respond to Clarifica | Bid Receive / Bid Opening | Tech. Evaluation | Final Evaluation | Con. Award | Con. Signed | Complete Works / Goods/ Services delivered | Remarks
1 | Construction of Livelihood Development Center Building J/69 | 2000000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 24.02.2020
2 | Construction of Valanpuram Beach Road Drainage. | 1770000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 17.03.2020
3 | Improvement of Columbuthurai 1,2,3,4 cross road | 230000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 17.03.2020
4 | Renovation of Ilanthaikulam inlet channel work - Phase I | 1360000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 18.02.2020
5 | Renovation of Ilanthaikulam inlet channel work - Phase II | 119300 | S | Community bassed Procurement
|  |  | A | [10 empty] | 18.02.2019
6 | Renovation of the Road infront of Ilanthaikulam Pillaiyar Temple. | 515000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 18.02.2020
7 | Providing purified water from Public Well (Drinking Water). |  | S | Community bassed Procurement
A
8 | Construction of Drinking Water Purification Center. |  | S | Community bassed Procurement
A
9 | Construction of Drinking Water Purification Center& Construction of water tank for fishermen (Water connection to Passaiyoor St.Antonys People Development Community Center) (Location J/64). | 2000000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 16.06.2020
10 | Construction of Vithanaiyar Road Sub lane drainage wall work. | 1449000 | S | Community bassed Procurement
A
11 | Renovation of Echchamoddai Beach Road Drainage. | 166515 | S | Community bassed Procurement
|  |  | A | [10 empty] | 20.02.2020
12 | Reconstruction of palassas lane aqueduct work. | 196730 | S | Community bassed Procurement
A
13 | Construction of Livelihood Development Center Building J/61 | 2000000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 24.02.2020
14 | Renovation of 1st, 2nd, 3rd lanes near flats. (Concrete Road) | 1510000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 18.02.2020
15 | Renovation of new housing scheme Drainage | 261200 | S | Community bassed Procurement
|  |  | A | [10 empty] | 18.02.2020
16 | Construction of Livelihood Development Center Building J/76 | 2000000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 24.02.2020
17 | Construction of Livelihood Development Center Building J/70 | 2000000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 12.03.2020
18 | Reconstruction of Gurunagar west villege internal flood canal work. (Adappan Road Drinage & 1st, 2nd lanes Drainages, Kodadi Road Internal Canal, Koddadi Road Canal & Pansal Road Canal) | 2000000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 12.03.2020
19 | Renovation of 4th Cross Road Drainage. | 2000000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 12.03.2020
20 | Renovation of Tharakulam Channel, 2nd Cross Road Drainage & 5th Cross Road Drainage. | 1899000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 04.03.2020
21 | Renovation of Madam Road (Vembady) Drainage Canal wall work. |  | S | Community bassed Procurement
|  |  | A | [10 empty] | 18.02.2020
22 | Improvenent of Martin Lane Bakery Lane Joint Road. | 783000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 22.06.2020
23 | Renovation of concret work of Drainage from Main Street to Maththyoos Road and connecting channel. |  | S | Community bassed Procurement
A
24 | Construction of Livelihood Development Center Building J/67 | 2000000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 24.02.2020
25 | Construction of Toilet & Providing Water Facilities for J/Nallur Vigneswara School. | 2000000 | S | Community bassed Procurement
A
26 | Construction of Livelihood Development Center Building J/78 | 2000000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 12.03.2020
27 | Renovation of Kalaipulavar Road Drainage. | 430300 | S | Community bassed Procurement
|  |  | A | [10 empty] | 18.02.2020
28 | Construction of drainage canal across the lane at sirampiyady lane. | 230000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 24.06.2019
29 | Construction of Livelihood Development Center for unemployed youth and women headed families to develop the SMEs like leather based, sawing and food processing and packing. |  | S | Community bassed Procurement
A
30 | Construction of Livelihood Development Center Building J/81 | 2000000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 24.02.2020
31 | Renovation of Pirappankulam Road (Concret Road). |  | S | Community bassed Procurement
A
32 | Construction of chainlink fence around the Katkulam Kulam. | 1630000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 26.05.2020
33 | Renovation of Vallantheru canal work | 323200 | S | Community bassed Procurement
A
34 | Renovation of Kannapuram 4th lane | 1576000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 19.02.2020
35 | Construction of Livelihood Development Center Building | 2000000 | S | Community bassed Procurement
A
36 | Renovation of Nedunkulam Work Osmaniya College Road | 1225000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 26.05.2020
37 | Renovation of Osmaniya College 1st Lane (right), 2nd Lane (left). | 1320000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 20.02.2020
38 | Construction of concrete road of Muslim College Road P.D Lane, Asath Road Savuthi Lane Sub Lane. | 605000 | S | Community bassed Procurement
|  |  | A | [10 empty] | 13.03.2020
39 | Renovation of Thurumpaikulam. | 1500000 |  | Community bassed Procurement
26.05.2020