## Sheet1
Action Plan for 1st Quarter of the Year 2019
Ministry of Home Affairs
Institution : Divisional Secretariat , Jaffna
Strategy No | Proposed Activity | Allocation (Rs.'000) | Date of commence | Date of completion | Financial Target (Rs.'000) Cumulative |  |  |  | Physical Target (%) Cumulative |  |  |  | Output Indicator | Implementing Agency | Respon- sible by | Contact no | Remarks
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Intercom | 102400 | 2019.02.01 | 2019.02.26 | Financial Target (Rs.'000) Cumulative Q1: 102400; Physical Target (%) Cumulative Q1: 100 | Intercom establishment | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
2 | Resettlement Assistant for refugee returnees | 456000 | 2019.02.25 | 2019.02.25 | Financial Target (Rs.'000) Cumulative Q1: 456000; Physical Target (%) Cumulative Q1: 100 | Renovation of well and land | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
3 | Sanitation Project | 1650000 | 2019.03.28 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q1: 450000; Financial Target (Rs.'000) Cumulative Q2: 1200000; Physical Target (%) Cumulative Q1: 27; Physical Target (%) Cumulative Q2: 73 | Construction of 30 toilet | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
4 | Permanent housing | 25518000 | 2019.03.08 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q1: 17200000; Financial Target (Rs.'000) Cumulative Q2: 8318000; Physical Target (%) Cumulative Q1: 67; Physical Target (%) Cumulative Q2: 33 | Construction of 47 houses | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
5 | Gramma Shakthy | 3137650 | 2019.03.07 | 2019.09.30 | 92075 | 2000000 | 1045575 |  | 3 | 64 | 33 |  | Development of 12 GS divisions | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
6 | development of safty centre | 1000000 | 2019.04.23 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q2: 1000000; Physical Target (%) Cumulative Q1: 0; Physical Target (%) Cumulative Q2: 100 | Construction of building | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469

## Sheet2
Action Plan for 3rd Quarter of the Year 2019
Ministry of Home Affairs
Institution : Divisional Secretariat , Jaffna
Strategy No | Proposed Activity | Allocation (Rs.'000) | Date of commence | Date of completion | Financial Target (Rs.'000) Cumulative |  |  |  | Physical Target (%) Cumulative |  |  |  | Output Indicator | Implementing Agency | Respon- sible by | Contact no | Remarks
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Sanitation Project | 2095500 | 2019.03.28 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q1: 450000; Financial Target (Rs.'000) Cumulative Q2: 1200000; Physical Target (%) Cumulative Q1: 27; Physical Target (%) Cumulative Q2: 73 | Construction of 30 toilet | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
2 | Permanent housing | 65056451.76 | 2019.03.08 | 2019.12.31 | Financial Target (Rs.'000) Cumulative Q1: 17200000; Financial Target (Rs.'000) Cumulative Q2: 47856451.76; Physical Target (%) Cumulative Q1: 67; Physical Target (%) Cumulative Q2: 33 | Construction of 47 houses | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469 |  | 199000000
3 | Gramma Shakthy | 3137650 | 2019.03.07 | 2019.09.30 | 92075 | 2000000 | 1045575 |  | 3 | 64 | 33 |  | Development of 12 GS divisions | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469 |  | 195775183.65
4 | development of safty centre | 1000000 | 2019.04.23 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q2: 1000000; Physical Target (%) Cumulative Q1: 0; Physical Target (%) Cumulative Q2: 100 | Construction of building | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
5 | Gamperaliya Construction | 199 Million | 2019.04.01 | 2019.08.31 |  | 3224816.35 | 195775183.65 |  | 0 | 1.62 | 98.4 |  |  | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
6 | Roof work | 2149000 | 2019.05.25 | 2019.06.20 | Financial Target (Rs.'000) Cumulative Q2: 2149000; Physical Target (%) Cumulative Q2: 100 |  | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
7 | Construction of Engine room | 750000 | 2019.05.01 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q2: 750000; Physical Target (%) Cumulative Q2: 100 |  | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
8 | Construction of cycle shed | 1890000 | 2019.05.01 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q2: 1890000; Physical Target (%) Cumulative Q2: 100 |  | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
I certify that the above particulars are correct.
Prepared By :
Checked By :
Divisional Secretary,
Divisional Secretariat,
Jaffna.

## 2019
Action Plan of the Year 2019
Ministry of Home Affairs
Institution : Divisional Secretariat , Jaffna
Strategy No | Proposed Activity | Allocation (Rs.'000) | Date of commence | Date of completion | Financial Target (Rs.'000) Cumulative |  |  |  | Physical Target (%) Cumulative |  |  |  | Output Indicator | Implementing Agency | Respon- sible by | Contact no | Remarks
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Intercom | 102400 | 2019.02.01 | 2019.02.26 | Financial Target (Rs.'000) Cumulative Q1: 102400; Physical Target (%) Cumulative Q1: 100 | Intercom establishment | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
2 | Resettlement Assistant for refugee returnees | 456000 | 2019.02.25 | 2019.02.25 | Financial Target (Rs.'000) Cumulative Q1: 456000; Physical Target (%) Cumulative Q1: 100 | Renovation of well and land | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
3 | Sanitation Project | 2095500 | 2019.03.28 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q1: 450000; Financial Target (Rs.'000) Cumulative Q2: 1200000; Physical Target (%) Cumulative Q1: 27; Physical Target (%) Cumulative Q2: 73 | Construction of 30 toilet | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
4 | Permanent housing | 65056451.76 | 2019.03.08 | 2019.12.31 | Financial Target (Rs.'000) Cumulative Q1: 17200000; Financial Target (Rs.'000) Cumulative Q2: 47856451.76; Physical Target (%) Cumulative Q1: 67; Physical Target (%) Cumulative Q2: 33 | Construction of 47 houses | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
5 | Gramma Shakthy | 3137650 | 2019.03.07 | 2019.09.30 | 92075 | 2000000 | 1045575 |  | 3 | 64 | 33 |  | Development of 12 GS divisions | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
6 | development of safty centre | 1000000 | 2019.04.23 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q2: 1000000; Physical Target (%) Cumulative Q1: 0; Physical Target (%) Cumulative Q2: 100 | Construction of building | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
7 | Gamperaliya Construction | 194370750 | 2019.04.01 | 2019.11.30 |  | 3224816.35 | 195775183.65 |  | 0 | 1.62 | 98.4 |  |  | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
8 | Roof work | 2149000 | 2019.05.25 | 2019.06.20 | Financial Target (Rs.'000) Cumulative Q2: 2149000; Physical Target (%) Cumulative Q2: 100 |  | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469 |  | 1.6591
9 | Construction of Engine room | 750000 | 2019.05.01 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q2: 750000; Physical Target (%) Cumulative Q2: 100 |  | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
10 | Construction of cycle shed | 1890000 | 2019.05.01 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q2: 1890000; Physical Target (%) Cumulative Q2: 100 |  | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
I certify that the above particulars are correct.
Prepared By :
Checked By : | [12 empty] | ……………………………
Divisional Secretary,
Divisional Secretariat,
Jaffna.

## 2019 summary
Action Plan of the Year 2019
Ministry of Home Affairs
Institution : Divisional Secretariat , Jaffna
Strategy No | Proposed Activity | Allocation (Rs.'000) | Date of commence | Date of completion | Financial Target (Rs.'000) Cumulative |  |  |  | Physical Target (%) Cumulative |  |  |  | Output Indicator | Implementing Agency | Respon- sible by | Contact no | Remarks
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Intercom | 102400 | 2019.02.01 | 2019.02.26 | Financial Target (Rs.'000) Cumulative Q1: 102400; Physical Target (%) Cumulative Q1: 100 | Intercom establishment | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
2 | Resettlement Assistant for refugee returnees | 456000 | 2019.02.25 | 2019.02.25 | Financial Target (Rs.'000) Cumulative Q1: 456000; Physical Target (%) Cumulative Q1: 100 | Renovation of well and land | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
3 | Sanitation Project | 2095500 | 2019.03.28 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q1: 450000; Financial Target (Rs.'000) Cumulative Q2: 1650000; Physical Target (%) Cumulative Q1: 27; Physical Target (%) Cumulative Q2: 100 | Construction of 30 toilet | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
4 | Permanent housing | 65056451.76 | 2019.03.08 | 2019.12.31 | Financial Target (Rs.'000) Cumulative Q1: 17200000; Financial Target (Rs.'000) Cumulative Q2: 65056451.76; Physical Target (%) Cumulative Q1: 67; Physical Target (%) Cumulative Q2: 100 | Construction of 47 houses | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
5 | Gramma Shakthy | 3137650 | 2019.03.07 | 2019.09.30 | 92075 | 2092075 | 3137650 |  | 3 | 67 | 100 |  | Development of 12 GS divisions | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
6 | development of safty centre | 1000000 | 2019.04.23 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q2: 1000000; Physical Target (%) Cumulative Q1: 0; Physical Target (%) Cumulative Q2: 100 | Construction of building | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
7 | Gamperaliya Construction | 294370750 | 2019.04.01 | 2019.11.30 |  | 3224816.35 | 109290944.77 | 261067152.64 | 0 | 2 | 62 | 97 | road, drainage,park,temple and playground | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
8 | Roof work | 2149000 | 2019.05.25 | 2019.06.20 | Financial Target (Rs.'000) Cumulative Q2: 2149000; Physical Target (%) Cumulative Q2: 100 |  | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
9 | Construction of Engine room | 750000 | 2019.05.01 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q2: 750000; Physical Target (%) Cumulative Q2: 100 |  | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
10 | Construction of cycle shed | 1890000 | 2019.05.01 | 2019.06.30 | Financial Target (Rs.'000) Cumulative Q2: 1890000; Physical Target (%) Cumulative Q2: 100 |  | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
11 | Renovation of Jetty at Gurunagar | 5726160 | 2019.09.25 | 2019.12.31 | Physical Target (%) Cumulative Q4: 100 |  | Divisional Secretariat Jaffna | Divisional Secretary | 22 222 8469
12 | IDP | 37600000 | 2019.08.01 | 2019.12.31 | Financial Target (Rs.'000) Cumulative Q3: 886000; Financial Target (Rs.'000) Cumulative Q4: 7644813.26; Physical Target (%) Cumulative Q3: 3; Physical Target (%) Cumulative Q4: 100 |  | Divisional Secretariat Jaffna | Divisional Secretary | 23 222 8469
I certify that the above particulars are correct.
Prepared By :
Checked By : | [12 empty] | ……………………………
Divisional Secretary,
Divisional Secretariat,
Jaffna.

## 2018
Action Plan of the Year 2019
Ministry of Home Affairs
Institution : Divisional Secretariat , Jaffna
Strategy No | Proposed Activity | Allocation (Rs.'000) | Date of commence | Date of completion | Financial Target (Rs.'000) Cumulative |  |  |  | Physical Target (%) Cumulative |  |  |  | Output Indicator | Implementing Agency | Respon- sible by | Contact no | Remarks
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Fence work for gs office | [12 empty] | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
2 | [13 empty] | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
3 | [13 empty] | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
4 | [13 empty] | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
5 | [13 empty] | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
6 | [13 empty] | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
7 | [13 empty] | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
8 | [13 empty] | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
9 | [13 empty] | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
10 | [13 empty] | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
I certify that the above particulars are correct.
Prepared By :
Checked By : | [12 empty] | ……………………………
Divisional Secretary,
Divisional Secretariat,
Jaffna.