## 1 quarter
Action Plan for 1st Quarter of the Year 2020
Ministry of Home Affairs
Institution : Divisional Secretariat , Jaffna
Strategy No | Proposed Activity | Allocation (Rs.'000) | Date of commence | Date of completion | Financial Target (Rs.'000) Cumulative |  |  |  | Physical Target (%) Cumulative |  |  |  | Output Indicator | Implementing Agency | Responsible by | Contact no | Remarks
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Toilet repair | 450000 | 01.03.2020 | 31.03.2020 | Financial Target (Rs.'000) Cumulative Q1: 450000; Physical Target (%) Cumulative Q1: 100 | Toilet repair | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
2 | Finger print machine | 32480 | 01.01.2020 | 31.03.2020 | Financial Target (Rs.'000) Cumulative Q1: 32480; Physical Target (%) Cumulative Q1: 100 | Finger print machine | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
3 | Muti media projector and screen | 199900 | 01.01.2020 | 31.03.2020 | Financial Target (Rs.'000) Cumulative Q1: 199900; Physical Target (%) Cumulative Q1: 100 | Muti media projector and screen | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
4 | RIDP | 2000000 | 01.01.2020 | 30.11.2020 | 500000 | 500000 | 1000000 |  | 25 | 25 | 50 |  | Road Construction & Providing electricity | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
5 | Sapiri gamak | 48000000 | 01.01.2020 | 30.11.2020 | 5000000 | 10000000 | 15000000 | 18000000 | 10 | 20 | 30 | 40 | 48 Projects | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
I certify that the above particulars are correct.
Prepared By :
Checked By : | [14 empty] | ……………………………….
Divisional Secretary,
Divisional Secretariat,
Jaffna.

## 2 quarter
Action Plan for 2nd Quarter of the Year 2020
Ministry of Home Affairs
Institution : Divisional Secretariat , Jaffna
Strategy No | Proposed Activity | Allocation (Rs.'000) | Date of commence | Date of completion | Financial Target (Rs.'000) Cumulative |  |  |  | Physical Target (%) Cumulative |  |  |  | Output Indicator | Implementing Agency | Responsible by | Contact no | Remarks
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Toilet repair | 450000 | 01.03.2020 | 31.03.2020 | Financial Target (Rs.'000) Cumulative Q1: 450000; Physical Target (%) Cumulative Q1: 100 | Toilet repair | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
2 | Finger print machine | 32480 | 01.01.2020 | 31.03.2020 | Financial Target (Rs.'000) Cumulative Q1: 32480; Physical Target (%) Cumulative Q1: 100 | Finger print machine | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
3 | Muti media projector and screen | 199900 | 01.01.2020 | 31.03.2020 | Financial Target (Rs.'000) Cumulative Q1: 199900; Physical Target (%) Cumulative Q1: 100 | Muti media projector and screen | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
4 | RIDP | 2943351.6 | 01.01.2020 | 30.11.2020 | 843351.6 | 0 | 0 |  | 25 | 25 | 50 |  | Road Construction & Providing electricity | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469
5 | Sapiri gamak | 15441170 | 01.01.2020 | 30.11.2020 | 921170 | 10000000 | 15000000 | 18000000 | 10 | 20 | 30 | 40 | 48 Projects | Divisional Secretariat Jaffna | Divisional Secretary | 021 222 8469